OBSERVATIONS AND RECOMMENDATIONS

Value for Money Audit

- The College implementation of the Expanded Students’ Grant-in-Aid Program for Poverty Alleviation (ESGP-PA) left much to be desired as for school year (SY) 2014-2015 the scholars were reduced from 20 to eight, while at the end of the current SY 2015-2016 only 33 out of the 35 grantees remained at end of school year due to failed grades, late releases of funds  and inability of PhilSCA to institute bridging program by providing remedial/mentoring program to cater to the special needs of the scholars required in the Joint Memorandum Circular No. 2014-1 dated February 3, 2014-Guidelines on the Implementation of the ESGP-PA.

  - Joint Memorandum Circular No. 2014-1 dated February 3, 2014 was issued on the implementation of the ESGP-PA (Program) of which the State Universities and Colleges (SUCs) is one of the implementers along with the Department of Social Worker and Development (DSWD), Commission on Higher Education (CHED) and the Department of Budget and Management (DBM). The Program aims to contribute to the National Government’s thrusts in effectively addressing poverty alleviation by increasing the number of graduates in higher education among poor households and to get these graduates employed in high-value added occupation in order to lift their families out of poverty and contribute to national development.

  - The Program was initially implemented in SY 2014-2015 of which under the Republic Act (RA) No. 10633 or the 2014 General Appropriations Act (GAA), the approved budget for its implementation amounted to P2,182,000.00 intended to cover the scholarship grants of the targeted 35 potential student-grantees for said school year.  Included in the approved budget are the 3 percent Administrative and Miscellaneous Cost (AMC) to cover expenses for monitoring activities such as office supplies and materials, hiring of project technical staff/s or job order, communication, transportation/travel, Information Technology (IT) equipment, remedial/ mentoring programs and meetings/orientations and assembly. Each grantee shall be entitled to a scholarship grant of P60,000.00 per academic year or P30,000.00 per semester to cover the costs of tuition and other school fees, textbooks/other learning materials and stipend.

  - For CY 2015, the College received the same amount of appropriations of P2,182,000.00 for the ESGP-PA which was included in RA No. 10651, the 2015 GAA, under its MFO 1: Higher Education Services intended for the student-grantees of SY 2015-2016. As audited, the total ESGP-PA appropriations amounted to P3,648,000.00 including the continuing appropriations of P1,466,000.00, of which P2,904,600.00 was obligated, leaving an unobligated balance of P743,400.00, as shown on the next page.

- Table 1.  2015 ESGP-PA Appropriation

| Particulars | Approved Budget CY 2015 | Obligations Incurred | Unobligated balance |
| --- | --- | --- | --- |
| Per Audit |  |  |  |
| Continuing Appropriation | 1,466,000.00 | 803,400.00 | 662,600.00 |
| Current Year’s Appropriation | 2,182,000.00 | 2,101,200.00 | 80,800.00 |
| Total | 3,648,000.00 | 2,904,600.00 | 743,400.00 |
| As reported in FAR 1 and 1a |  |  |  |
| Continuing Appropriation | 1,269,108.87 | 803,400.00 | 465,708.87 |
| Current Year’s Appropriation | 2,182,000.00 | 2,101,200.00 | 80,800.00 |
| Total | 3,451,108.87 | 2,904,600.00 | 546,508.87 |
| Discrepancy-error in FAR 1 and 1a | 196,891.13 | - | 196,891.13 |

  - The discrepancy of the same amount of P196,891.13 on the data for approved budget and the unobligated balance for the continuing appropriation was due to erroneous reporting in the FARs 1 and 1a of ESGP-PA continuing appropriation at the start of CY 2015. Per audit,  the balance should be P1,466,000.00 arrived at by deducting the total obligations incurred in CY 2014 of only P716,000.00 from the appropriation of P2,182,000.00. It was erroneously reported as P1,269,108.87 consisting of P803,400.00 unobligated ESGP-PA balance as of December 31, 2014 and other MOOE budget of P465,705.87.

  - Verification on the implementation of the Program disclosed, as shown in the table below, that the College, as one of the participating SUCs,  has reached the targeted potential student-grantees of 35 in the 1st semester of SY 2015-2016 but was reduced to 33 in the 2nd semester of SY 2015-2016. While there was a total of 12 scholars in SY 2014-2015 who were replaced/removed in SY 2015-2016 due to failing grades or not enrolled because of personal reasons. Though it was not a ground for removal from the Program, it was the internal policy of the College to exclude students from any scholarship program if grantee has failed subjects as mentioned by the Scholarship Coordinator.

- Table 2.  Enrolled ESGP-PA Scholars

| No. of identified scholars | Enrolled in SY 2014-2015 |  | Enrolled in SY 2015-2016 |  | Not – Enrolled/ Failed/ Replaced |
| --- | --- | --- | --- | --- | --- |
|  | 1st Sem | 2nd Sem | 1st Sem | 2nd Sem |  |
| Scholars SY 2014-2015 | 20 | 20 | 11 | 8 | 1-VAB; 7-FAB; 1-BAB in 1st semester SY 2014-2015 and 2-VAB; 1-FAB |
| Additional scholars SY 2015-2016 |  |  | 24 | 25 |  |
| Total | 20 | 20 | 35 | 33 |  |

  - Further, it was noted that the College was not able to institute as needed, a bridging program to provide remedial/mentoring program to cater to the special needs of the student-grantees which is one of the responsibilities of PhilSCA as one of the implementers of the program as provided for in item 8.4.8 of the CHED, DBM, PASUC, DSWD and DOLE Joint Memorandum Circular No. 2014-1 dated February 5, 2014.

  - Moreover, it was learned, thru the questionnaires distributed to grantees by the audit team, that the common reasons for the dropping outs were due to financial and family problems. The delay in the release of funds is contributory factor in the school performance of the grantees. For SY 2014-15, the advice of NCA amounting to P803,400.00 for the remaining 13 enrolled student-grantees were issued by DBM only on July 15, 2015. Hence, payments of Scholarship benefits were paid to grantees on July 30, 2015. While, it was only on December 23, 2015 and March 18, 2016 that the payments amounting to P1,319,400.00 and P760,000.00, respectively, to the grantees for SY 2015-2016 have been made since Management was waiting for the release of specific NCA for the program.  Unlike in the first year of implementation of the ESGP-PA whereby DBM released a separate NCA specifically for the program, it was lately learned by Management from the DBM that the cash allocation for the program was already included in the NCAs received by PhilSCA.

  - There was another transfer of funds from Fund 101 under Check No. 84359 dated July 30, 2015 in favor of PhilSCA Fund Account Local Fund 164 (PhilSCA LCCA -Acct#3562-1003-25) in the amount of P283,400.00 to cover benefits for the remaining 13 grantees of SY 2014-2015 which were already paid per Check No. 59860 dated December 23, 2014 also from Fund 101. Hence, the additional fund transfer still in the PhilSCA Fund Account Local Fund 164 (PhilSCA LCCA -Acct#3562-1003-25) is considered as excess cash allocation.

  - As of December 31, 2015, there was total disbursements of P1,319,400.00 from the total obligations of P2,101,200.00 made from the current appropriations.  On March 18, 2016, a total of P760,000.00 was disbursed for the student grantees of VAB Campus; while the remaining balance of P21,800.00 was for the tuition fees of the two student grantees from FAB Campus and for administrative cost as shown below:

- Table 3.  Unpaid Tuition Fee and Administrative Cost

| No. | Name of Grantee | Year/ Course | Tuition Fee | Administrative Cost | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Valencia, Manolito L. | 2nd Yr AAMT | P10,000.00 – 1st sem. SY 2015-2016 | P 900.00 (P30,000.00/sem. x 3%) | 10,900.00 |
| 2 | Perez, Tom V. | 3rd Yr BSAMT | P10,000.00 – 2nd sem. SY 2015-2016 | 900.00 (P30,000.00/sem. x 3%) | 10,900.00 |
|  |  |  |  | Grand Total | 21,800.00 |

  - We recommended that the Management:

- continuously monitor the academic performance of the Program grantees and conduct remedial and mentoring programs to cater to the special needs of the students-grantees;

- coordinate with the DSWD, CHED, DBM and DOLE, the other key players/implementers of the Program to address the delay in the release of benefits,  and other issues preventing the efficient and effective implementation of the program;

- require the Accountant and the Scholarship Coordinator to have a database on scholarship to prevent occurrence of double charges from cash allocation, and revert back to BTr the excess cash allocation of P283,400.00; and

- require the Budget Officer to be accurate in reporting of budgetary data.

Tulong Dunong Scholarship Program

- The implementation of the Tulong Dunong Program incurred delays in the selection of scholars due to confusion on the actual allocation per legislator and absence of internal guidelines resulting to the non-utilization of the entire allotment of P324,000.00 as of December 31, 2015, hence depriving the scholars of the much needed financial assistance.

- Under the General Appropriations Act (GAA) for FY 2015, PhilSCA has an appropriations for Tulong Dunong amounting to P324,000.00 which was included in the MFO 1 Higher Education Services’ total appropriations of P47,642,000.00. The said grant is intended for the tuition and other fees of scholars for AY 2015-2016.

- The total amount of P324,000.00 was allocated by the DBM to the three members of the House of Representatives intended for the scholarship grants of their constituent beneficiaries. As mentioned by the Scholarship Coordinator of the College, PhilSCA was advised by Cong. Jonathan A. Dela Cruz (representative, ABAKADA Partylist) and Cong. Gustavo S. Tambunting (representative, 2nd District of Parañaque) to do the selection, screening, and determination of the number of grantees and the amount of grant to each student as the recipients of their allocation as approved by them. Only Cong. Elenita Milagros “Eileen” Ermita-Buhain endorsed the grantees for her allocation. The amount of allocation per legislator is computed at P6,000.00/ semester or P12,000.00/SY for each grantee, broken down as follows:

- Table 4.  List of Legislator and their Grantees

| No. | Name of Legislator | Number of Grantees | Date of Submission of the List of Grantees by the Office of Legislators | Amount of Allocation |
| --- | --- | --- | --- | --- |
|  | NCR |  |  |  |
| 1 | Tambunting, Gustavo S. | 17 | * | 200,000.00 |
|  | Region IV-A |  |  |  |
| 2 | Ermita-Buhain, Eileen | 2 | September 21, 2015 | 24,000.00 |
|  | Partylist |  |  |  |
| 3 | Dela Cruz, Jonathan A. (ABAKADA) | 8 | * | 100,000.00 |
|  | Total | 27 |  | 324,000.00 |

*Scholarship Coordinator was not able to provide the actual date of submission of the letter submitted to PhilSCA thru electronic mail

- The Scholarship Coordinator of the College commented that they have difficulty in contacting the legislators resulting in the delay in the submission of the lists of prospective grantees by the legislators. Also, there was a confusion on the actual fund allocation for Cong. Dela Cruz, whether P250,000.00 or P100,000.00 which caused further delay in the submission thereof. Considering that the Tulong Dunong Scholarship Program is intended for AY 2015-2016, the list of the pre-selected scholars should have been submitted months before the start of the first semester in June 2015 or second semester in October 2015 of AY 2015-2016 in order to give the Scholarship Office sufficient time for the implementation of the program.

- She further informed the Audit Team that, it was only on March 2016 that the Scholarship Office was advised by the CHED to make its own internal policy for the implementation of its Tulong Dunong Scholarship Program. Thus, in the absence thereof, PhilSCA adopted the CHED Memorandum Order No. 13 Series of 2014 or the revised guidelines for the implementation of the Student Financial Assistance Programs (StuFAPs), effective Academic Year (AY) 2014-2015 with the following applicable provisions:

- Section 2.2 -  Grants-in-Aid

Tulong Dunong is intended for:

  - high school graduates whose General Weighted Average (GWA) is at least a passing grade and for graduating high school students whose GWA is at least a passing grade in the third year and in the first three grading periods of the fourth year and who will enroll in identified priority courses in duly authorized public or private Higher Education Institutions (HEIs);

  - students with earned units in college whose weighted average is at least a passing grade for the last two (2) semesters and enrolled in identified priority courses in duly authorized public or private HEIs; and

  - students who passed the Alternative Learning System (ALS) and Philippine Educational Placement Test (PEPT).

- Section 3 - qualification requirements for student applicants are the following:

  - must be a Filipino citizen;

  - must be a high school graduate; candidate for graduation; with earned units in college; passer of ALS/PEPT;

  - must have a combined annual gross income of parents/guardian not to exceed Three Hundred Thousand Pesos (P300,000.00);

  - must avail of only one CHED scholarship or financial assistance program; and

  - must not be a graduate of any degree program.

- Section 6 further states that the package of financial assistance to grantees shall cover the completion of the degree program. The financial benefits per AY for Tulong Dunong is either P6,000.00, P9,000.00, or P12,000.00 depending on the tuition and other fees of the HEIs.

- Furthermore, it was noted that there was no Memorandum of Agreement (MOA) between PhilSCA and the three legislators. Only Cong. Ermita-Buhain indicated the amount of grant for each scholar as per the certification obtained by PhilSCA from CHED. For the remaining two legislators, it was PhilSCA that determined the amount.

- As a result of the foregoing deficiencies, the total allotment for this Program of P324,000.00 was not utilized as of December 31, 2015. Despite the submission of the list of grantees from Cong. Ermita-Buhain, no student has received the scholarship grants for the year 2015.

- There were no specific NCAs released by DBM to cover the Tulong Dunong Program. Per Accounting staff inquiry with the DBM, the cash allocation for the Tulong Dunong Scholarship Program was already included in the NCAs received by PhilSCA though not specifically indicated in the purpose section of each advice of NCA.  It was only on March 17, 2016 that the 27 checks totaling P244,204.00 were prepared charged against the General Fund – MOOE of PhilSCA for the payments to the grantees of the said program. The remaining balance of P79,796.00 from the total appropriations of P324,000.00 was for payment to PhilSCA of the unpaid tuition fees of grantees which was directly deducted from the P12,000.00 grant of each scholar. The said balance was still to be paid to PhilSCA.

- We recommended that Management initiate action to come up with its own internal policy to implement the Tulong Dunong Scholarship Program effectively and efficiently; and make representation with the Office of the Legislators to promptly submit their list of scholars.

- Management commented that PhilSCA has existing internal policy on scholarship grant including Tulong Dunong Program. No matter how many scholarship policies shall be reviewed and enhanced, the fact remains that all SUCs including PhilSCA is dependent on the allocation to be awarded to the SUCs by the legislator.

- The team maintains their observation that no internal policy and procedures were instituted in the implementation of Tulong Dunong Scholarship Program as stated on March 2016 by the Scholarship Coordinator that she was advised by CHED to make its own internal policy for the implementation of its Tulong Dunong Scholarship Program.

- Special Trust Fund

- The details of the approved Special Trust Fund (STF) budget of P125,653,420.84 as well as other required information were not indicated in both the Summary of Approved Budget, Utilizations, Disbursements and Balances (SABUDB) and Summary of Approved Budget, Utilizations, Disbursements and Balances by Object of Expenditures (SABUDBOE) for 2015 rendering these reports unreliable and preventing determination if the obligations incurred were within the amounts per class/object of expenditure.

- Sections 4.5 and 4.6 of COA and DBM Joint Circular No. 2014-1 dated July 2, 2014 prescribes the use of the SABUDB, FAR No. 2 which reflect the approved budget, utilizations, disbursements and balances of the agency authorized by law to use their income such as OWWA/SUCs, and approved by the Board of Trustees/Regents, while SABUDBOE, FAR No. 2 (A) (for Off-Budget Fund) reflect the details of approved budget, utilizations, disbursement and balances of the agency authorized by law to use their income presented by object of expenditures consistent with COA Revised Chart of Accounts.

- The total STF budget of P125,653,420.84 was approved and confirmed by the PhilSCA’s Board of Trustees thru Resolution No. 84, s. 2015 during its second regular meeting on June 26, 2015.

- The SABUDB (FAR No. 2) as of December 31, 2015 showed as follows:

Table 5.  SABUDB as of December 31, 2015

| Particulars | Approved Budget | Utilization | Unutilized Budget | Percent of Utilized Budget |
| --- | --- | --- | --- | --- |
| Personnel Services (PS) | - | 9,378,857.92 | (4,264,977.84) |  |
| Maintenance and Other Operating Expenses (MOOE) | - | 98,042,585.02 | (40,510,061.63) |  |
| Capital Outlays (CO) | - | 5,008,538.33 | (938,325.45) |  |
| Total | 125,653,420.84 | 112,429,981.27 | 13,223,439.57 | 89 |

- As clearly shown in above table, the allocated budget for each of the PS, MOOE and CO were not indicated in the report, only the utilized and unutilized budgets for each class of expenditure were shown.  Further review of the SABUDB showed the following observations:

  - Column 1 (Particulars) was not properly filled up.  It was not presented by Program/Activity/Project (PAP), which are the General Administration and Support (GAS) and Operations, but only by the major allotment class, PS, MOOE and CO.  The Major Final Output (MFO) which should have been appropriately placed under the caption “Operations” was also not disclosed separately.  The PS, MOOE and CO pertaining to GAS, Support to Operations and Operations should be categorized accordingly; and

  - The Unified Account Code System (UACS) codes were not also shown under Column 2 (UACS Code).

- On the other hand, our review of the SABUDBOE disclosed the following deficiencies:

  - Incorrectly named as Summary of Approved Budget, Utilizations, Disbursements and Balances instead of Summary of Approved Budget, Utilizations, Disbursements and Balances by Object of Expenditures;

  - The allocated budget for each object of expenditure was not reflected under Column 3 (Approved Budget Revenue) instead only the total budget of P125,653,420.84 was indicated;

  - The approved budget, utilization and disbursements for Fiduciary Fees, Other Fiduciary Fees, Research Services, Extension Services, Production, Administrative Services and Mandatory Reserve were not separately shown.  The report on the proposed budgetary allocation included fiduciary fees of P21,707,477.00; Other Fiduciary Fees of P35,617,595.58; Research Services, Extension Services, Production, Administrative Services and Mandatory Reserve of P6,832,834.83 each in addition to instruction services of P34,164,174.13; and

- Since the budget for each item of expenditure was not indicated, the total of unutilized budget resulted in a negative balance.

- We recommended that Management correctly and completely provide the data required in the SABUDB and SABUDBOE by including the detailed budget of each class/item of expenditure, UACS codes, among others, in compliance with the format and instructions in filling up these reports. Those pertaining to Fiduciary Fees and Other Fiduciary Fees should be separately shown in order to facilitate monitoring of their utilization.

Utilization of STF budget for Research Services

- PhilSCA failed to substantially discharge its research services function as shown by the low rate of 19 percent utilization of its budget of P6,832,834.83, non-completion of the five BOT approved proposals,  failure to undertake the budgeted activities, and the Research Council non convening since last year, contrary to its mandated function and mission that could be a minus factor in the leveling of the College.

- PhilSCA Research and Development Center (RDC) has the following vision, mission and goals and objectives:

- Vision:  PhilSCA shall be the leading research engine in aeronautical technology in the country responding to society’s needs of improving the aviation industry to satisfy demands for better quality and safety in air transportation.

- Mission:  To generate and disseminate knowledge in the aeronautical sciences through meaningful, and challenging research programs in aircraft design and innovations,  maintenance and operations and aviation information technology for the benefit of the people and the society.

- Goals and Objectives:

- Strengthen R & D capabilities in terms of both manpower and research facilities as a strategy for long-term excellence and competitiveness.

- Establish research culture by promoting and enhancing research awareness among faculty members and students.

- Provide financial support through research and scholarship grants.

- Encourage research collaboration and cooperation among members of the academic community and other institutions locally and internationally.

- Conduct relevant and high impact researches in the fields of Aeronautical education.

- Moreover, PhilSCA Research Manual provides the creation of a Research Council with the following functions:

  - Established research priorities from the College;

  - Formulating and recommending research policies and strategies to achieve institutional plan;

  - Coordinating all activities of the faculties and staff;

  - Reviewing research proposals and recommending funding;

  - Regulating research activities;

  - Reviewing research results for publication; and

  - Conducting periodic evaluations of the research activities of the College and submit recommendations to the President.

- Since CY 2011 PhilSCA has no appropriation for research services under the GAA although it is one of the trifocal functions of the state universities and colleges. Thus, from the P400,000.00 STF budget in CY 2014, Management increased to P6,832,834.83 the budget for research programs, per BOT approved STF budget in CY 2015. This budget was allocated to the four PhilSCA campuses for the following projects/activities:

Table 6.  Budget Allocation per PhilSCA Campus

| Projects/Activities | Villamor Air Base (VAB) | Fernando Air Base (FAB) | MBE Air Base (MAB) | Basa Air Base (BAB) | Total |
| --- | --- | --- | --- | --- | --- |
| Staff Development | 1,000,000.00 | 250,000.00 | 350,000.00 | 250,000.00 | 1,850,000.00 |
| Research and Development | 1,250,000.00 | 250,000.00 | 350,000.00 | 250,000.00 | 2,100,000.00 |
| Seminar Workshop | 1,250,000.00 | 200,000.00 | 300,000.00 | 300,000.00 | 2,050,000.00 |
| Equipment | 279,105.59 | 276,509.61 | 138,094.09 | 139,125.55 | 832,834.84 |
| Total | 3,779,105.59 | 976,509.61 | 1,138,094.09 | 939,125.55 | 6,832,834.84 |

- Notwithstanding the increase in the research services budget, still these five projects in CY 2013 which were approved by the BOT under Resolution No. 25 series of 2013 as recommended by the PhilSCA Research Council have not been completed to date allegedly because these were not funded and due to procurement problems encountered by proponents, hence the failure of PhilSCA to realize the purpose for these projects.

Table 7.  List of CY 2013 Unaccomplished Research Projects

| Project No. | Title of Research Projects | Budgetary Requirements | Timelines | Proponents |
| --- | --- | --- | --- | --- |
| 1 | Marshalling the Landscape of Aviation Education in the Philippine Context | P130,000.00 | Not stated | Mr. Victor P. Estrella, Mr. Patrick John F. Mansueto, and Ms. Mary Rose Tacedena |
| 2 | A study on the Reactions and expectations of the new students in enrolling at the Philippine State College of Aeronautics | 50,000.00 | May 1 to Oct 21, 2013 | Dr. Roderick C. Santiago, Dr. Estrella E. Yago, and Dr. Elisa F. Grampil |
| 3 | Performance in the Aeronautical Engineering Board Examination for the Last Five Years: Trends, Issue and Future Directions | 50,000.00 | Not stated | Mr. Joseph Christian P. Barrientos, Mr. Odysseus Ivan F. Celis, Mr. Marlon Jetro C. Cortez, Mr. Joefreim A. Delicano, Mr. John Kevin M. Dizon and Mark Joel L. Olfindo |
| 4 | An assessment of the Manifestation of PhilSCA –VAB Vision, Mission, Goals and Objectives to Meet the Course Outcomes of the CMO 28 for Aeronautical Engineering | Not stated | Not stated | Mr. Romick B. Medina |
| 5 | Calibrated Gear System for Applied Wooden Wing Rib Stress Tester | Not stated | Not stated | Mr. Guiseppe Andrew B. Buffe, Mr. Barry Christian T. Cutar, Ms. Ma. Agatha N. Destreza, Mr. Mark David H. Manicio, Mr. John Paul B. Migriño, Mr. Dan Josjua L. Patawe, Mr. Jenesis B. Suministrado and Mr. Jeffrey R. Villarroya |

- Further, not all of the following proposed Research Plans and Programs in CY 2015 submitted by the Acting Director of Research and Development Center were accomplished. According to inquiry from the Acting Vice President of Administration and Finance, it was not approved by the PhilSCA Research Council and Board of Trustees. Further, the audit team learned from one of the members of Research Council that the Council has not convened since last year.

- Table 8. 2015 Unapproved Research Plan and Programs

| Plans/Programs/Activities | Time Frame | Budgetary Requirement |
| --- | --- | --- |
| PhilSCA Research Colloquia | January 2015- July 2015 | 100,000.00 |
| PhilSCA Research Capability Building Series: Research Writing Seminar/workshop | February 2015 | 50,000.00 |
| PhilSCA Research Capability Building Series: Student Research Congress | March 2015 | 60,000.00 |
| Release of Research Funding for BOT Approved Researches | March 2015 | 880,000.00 |
| PhilSCA Research Paper Presentation in Local/National/International Fora | April 2015 | 200,000.00 |
| PhilSCA Research Capability Building Series: Refereeing and Publishing Research Outputs | May 2015 | 100,000.00 |
| PhilSCA Research Project Proposals | June 2015 | 600,000.00 |
| PhilSCA Research Capability Building Series : Retooling of Thesis Advisers and Panel Members and Statistical Analysis in Research | July 2015 | 100,000.00 |
| PhilSCA Research Journal Publication | October 2015 | 75,000.00 |
| PhilSCA Research Paper Award Selection | November 2015 | 150,000.00 |
| Presentation of Research Outputs in National/ International Research For a Presentation in International Higher Education Research Forum 2015 | January-December 2015 | 200,000.00 |
| Research Paper Publication in National/ International Research Journals | January-December 2015 | 100,000.00 |
| Food Expenses for Meetings and Transportation | January-December 2015 | 40,000.00 |
| Procurement of Equipment | January-December 2015 | 490,000.00 |
| Personal Services | January-December 2015 | 423,000.00 |
| Supplies and Materials | January-December 2015 | 100,000.00 |
|  | Total | 3,668,000.00 |

- On the financial aspect, it was also observed the low utilization of the budget for research services, which is measly 19 percent of the budget, where:

Table 9.  Utilization of Research Budget Per Campus

| Particulars | VAB | MAB | FAB | BAB | Total |
| --- | --- | --- | --- | --- | --- |
| ALLOCATION PER CAMPUS | 3,779,105.58 | 1,138,094.09 | 976,509.61 | 939,125.55 | 6,832,834.83 |
| Expenses incurred: |  |  |  |  |  |
| Total travelling Expenses | 130,773.00 | 285,444.68 |  |  | 416,217.68 |
| Total reimburse-ment of expenses on research seminar attended |  | 9,799.36 |  |  | 9799.36 |
| Total reimburse-ment of expenses related to research | 26,949.00 | 34,365.16 |  | 440.00 | 61,754.16 |
| Total expenses of Research and Development Office | 448,436.25 | - |  |  | 448,436.25 |
| Total compensation of Research Analyst | 27,041.64 | 62,613.07 |  |  | 89,654.71 |
| Payment for the seminar workshop "Research Paper Presentation” | - |  | - | 49,470.00 | 49,470.00 |
| Payment for the purchase of various supplies and materials | 145,236.00 |  |  |  | 145,236.00 |
| Payment for the registration fee PASUC NCR Research Consortium | 35,000.00 |  |  |  | 35,000.00 |
| Payment for the honorarium during the conduct of refereeing of PhilSCA Journal | 18,000.00 | - |  |  | 18,000.00 |
| Payment of registration fee of participants to Nakem Conference International | - | 9,800.00 | - |  | 9,800.00 |
| Total Fund Utilization | 831,435.89 | 402,022.27 | - | 49,910.00 | 1,283,368.16 |
| Unutilized STF budget for Research Services | 2,947,669.69 | 736,071.82 | 976,509.61 | 889,215.55 | 5,549,466.67 |
| Percentage of Utilization | 22% | 35% | 0% | 5% | 19% |

- We recommended and Management agreed to strengthen PhilSCA’s research services thru the RDC and the Research Council by assessing its research program strategy towards the efficient implementation of the planned research programs/projects/activities and proposals. Prioritize the completion of the five approved research proposals if the outcome thereof will benefit PhilSCA and the aviation industry. Likewise, maximize the utilization of the budget as planned in accordance with existing rules and regulations.

- Financial and Compliance Audit

Unreliable Property, Plant and Equipment (PPE) accounts balances

- The total PPE accounts costing P410,872,059.87 is unreliable due to:                  a) difference of P1,291,895.00 between the General Ledger (GL) balance of  P410,872,059.87 and the Schedules (serve as Subsidiary Ledgers) totaling P409,580,164.87; b) six buildings and parking facility constructed by a private corporation in 2010 not yet recorded in the books; c) incomplete physical inventory of PPE conducted in 2015, with no Report on the Physical Count of Property, Plant and Equipment (RPCPPE) rendered by Property and Supply Office on the existence and condition of the assets; and d) PPELC and Property Cards (PC) which should provide information on the acquisition/disposal for each PPE were incomplete or not updated, hence, unreliable references for reconciling balances of both records.

- Section 2, Chapter 2, General Provisions, Basic Standards and Policies of GAM Volume I requires the Subsidiary Ledger (SL) as  one of the books of accounts and registries of the National Government entities.  The SL shows detail for each control account in the GL which is maintained per account and fund cluster by the Accounting Division/Unit. At the end of each month, after all transactions in the journals have been posted, the debit and credit columns of each account shall be footed in pencil and the balance indicated in ink.  The totals of the SL balances shall be reconciled with the corresponding GL controlling account.  At the end of the year, each SL shall be ruled and closed.  All totals shall be written legibly in ink and the balance of the account carried forward as the opening balance of the new SL for the next fiscal year.

- As of December 31, 2015, the PPE accounts had a total recorded acquisitions amounting to P410,872,059.87, of which various equipment of P4,337,393.33 were procured in 2015.

- The total PPE cost of P410,872,059.87 per GL compared to the subsidiary schedules of P409,580,164.87 had a discrepancy of P1,291,895.00, details are shown in the table below:

- Table 10. Comparison Between Summary Per General Ledger (GL) and Subsidiary Ledgers

| - Type of PPE | - Summary per - (General Ledger) | - Summary per Schedules (Subsidiary Ledger) | - Difference |
| --- | --- | --- | --- |
| - Land | - 255,000,000.00 | - 255,000,000.00 | - 0.00 |
| - School Buildings | - 31,609,215.50 | - 31,609,215.50 | - 0.00 |
| - Other Structure | - 6,977,372.74 | - 6,977,372.74 | - 0.00 |
| - Office Equipment | - 20,918,532.72 | - 20,089,337.72 | - 829,195.00 |
| - Furniture and Fixtures | - 8,813,871.72 | - 8,813,871.72 | - 0.00 |
| - IT Equipment and Softwares | - 31,388,655.08 | - 30,729,355.08 | - 659,300.00 |
| - Library Books | - 1,731,140.00 | - 1,731,140.00 | - 0.00 |
| - Communication Equipment | - 1,541,515.00 | - 1,750,815.00 | - (209,300.00) |
| - Disaster Response and Rescue Equipment | - 292,800.00 | - 292,800.00 | - 0.00 |
| - Medical, Dental and laboratory Equipment | - 406,800.00 | - 406,800.00 | - 0.00 |
| - Sports Equipment | - 316,652.00 | - 303,952.00 | - 12,700.00 |
| - Technical and Scientific Equipment | - 21,566,884.43 | - 21,566,884.43 | - 0.00 |
| - Other Machineries and Equipment | - 3,511,449.05 | - 3,511,449.05 | - 0.00 |
| - Land Transport Equipment/Motor Vehicles | - 11,761,376.30 | - 11,761,376.30 | - 0.00 |
| - Aircrafts/Aircraft Ground Equipment | - 13,995,773.33 | - 13,995,773.33 | - 0.00 |
| - Other Property, Plant and Equipment | - 1,040,022.00 | - 1,040,022.00 | - 0.00 |
| - Totals | - 410,872,059.87 | - 409,580,164.87 | - 1,291,895.00 |

- Four PPE accounts were noted with discrepancies between the GL and the schedules. Details of the discrepancies, however, were not ascertained due to the unreliability of the supporting schedules as references.  Instead of the required PPELC as subsidiary records, the Accounting just maintained soft copies in MS Excel format of the PPE schedules and such served as their references for the details of the costs of each PPE items, which were provided to the Audit Team.

- Inadequate Accounting and Property Records

- Section 42, Chapter 10, PPE of GAM Volume I provides that the Chief Accountant shall maintain the PPELC for each category of PPE. The PPELC shall be kept to record promptly the acquisition, description, custody, estimated useful life, depreciation, impairment loss, disposal and other information about the asset. For check and balance, the Property and Supply Office/Unit shall likewise maintain PC for PPE in their custody to account for the receipt and disposition of the same. The balance per PC shall be reconciled with PPELC maintained by the Accounting Division/Unit. They shall also be reconciled with other property records like PAR.

- The Property Cards maintained by the Supply/Property Officer are incomplete.  In Villamor Air Base Pasay campus, only those PPE acquired up to CY 2013 were covered by PC and only for some equipment in CY 2014 and none for CY 2015.  Their reason was that the person in charge has already resigned from the office.

- As to the PPELC, the Accountant provided the audit team soft copies thereof in MS Excel format which serve as their references because they are not maintaining or preparing PPELC;

- Non-maintenance of the PPELCs and PCs by both Units diminishes the available techniques of verifying the accuracy of the reported total amount of PPE in the books.

- Unrecorded Buildings and Other Facilities

- On June 10, 2010, a Memorandum of Agreement (MOA) was executed and entered into by the PhilSCA, BCDA and Megaworld Corporation whereby PhilSCA agreed to transfer from the PhilSCA Villamor Air Base Pasay Campus to the new PhilSCA relocation site.  In November 2010, the College transferred to the new site at Piccio Garden, Villamor, Pasay City (in front of South Luzon Expressway Sales Exit).

- Among the salient features of the MOA was that Megaworld shall assume all expenses in the relocation and replication of the PhilSCA’s classrooms, offices, and other facilities at the old site and in compliance therewith, MEGAWORLD constructed the following structures in the new relocation site:

- Main Building 1 – 4 storey

- Building 2 – 4 storey

- Hangar Building – 2 storey

- Quarters Building – 2 storey

- One storey dormitory

- Flight Simulator Building

- Parking facility

- In November 2010, PhilSCA occupied the buildings constructed by the MEGAWORLD. No data however, was provided by the Megaworld Corporation as to the valuation of the said constructed buildings for purposes of reporting/recording the property values.  As of December 31, 2015, the acquired PPE were still unrecorded in the books of the PhilSCA, hence understating the respective PPE accounts balances. The same findings were already noted and reported in the Annual Audit Report for the years 2011 to 2013.

- According to the PhilSCA Management, there is a need for the development and building/structure plans, detailed construction cost per building/ structure and other pertinent documents from the MEGAWORLD as basis for the issuance of the certificate of acceptance and recording thereof.

- On February 23, 2016, the Director for Institutional Development Planning of this College has requested BCDA for the latest cost valuation of buildings and equipment turned over to PhilSCA.  In a letter dated March 30, 2016, the BCDA stated that based on their Joint Venture Agreement with Megaworld Corporation, PhilSCA was included in the list of Structures for Replications with an approved budget of P56.55M.  For the meantime, BCDA cannot provide the requested detailed information about the valuation of the buildings and equipment turned over to PhilSCA.

- Incomplete Physical Inventory of PPE

- Section 38, Chapter 10, Property, Plant and Equipment of GAM Volume 1 states that the entity shall have a periodic physical count of PPE, which shall be done annually and presented on the Report on the Physical Count of Property, Plant and Equipment (RPCPPE) (Appendix 71) as at December 31 of each year. This shall be submitted to the Auditor concerned not later than January 31 of the following year. Equipment found at station and losses discovered during the physical count shall be reported to the Accounting Division/Unit for proper accounting/recording.

- Management has undertaken physical count in 2015 of PPE, but only for PPE acquired in 2014 and prior years. Inventory of 2015 acquisitions started only this March 2016 and is still on going.

- The Property and Supply Office has submitted to the COA Audit Team on October 7, 2015 the RPCPPE covering only CY 2014. The RPCPPE, however, cannot be relied upon because they are not reconciled even with the 2014 PPE book balances; certain PPE items have not indicated acquisition costs or assigned values; and not classified to the proper PPE account, hence the existence and condition of the PPE assets was not ascertained.

- We recommended that Management:

- reconcile the records between General Ledger and subsidiary ledgers;

- require the Accounting Section and Supply/Property Section to maintain an updated PPELC and Property Records to facilitate reconciliation of records;

- engage the services of an independent appraiser to appraise the cost and structural integrity/soundness of the buildings and structures as basis in the issuance of certificate of acceptance,  recording in the books and other possible action of PhilSCA to correct any noted defects in the structural integrity of the buildings, and

- expedite the completion of the inventory taking and accomplish completely the report thereon, ensure that the records of the Accounting Section and Supply/Property Section are regularly reconciled to come up with accurate property records and PPE balances and establish the integrity of property custodianship.

Unremitted collection from performance bond to BTr

- PhilSCA did not remit to the Bureau of the Treasury (BTr) the amount of P593,777.65 as of December 31, 2015 consisting of collections from performance bonds and bid documents contrary to the provisions of Section 6 of the General Provisions of FY 2015 General Appropriations Act (GAA).

- Section 6 of the General Provisions of FY 2015 GAA provides that, “xxx Performance bonds and deposits filed or posted by private persons or entities with agencies of the Government shall be deposited with the National Treasury as trust receipts under the name of the agency concerned in accordance with E.O. 338 series of 1997. Upon faithful performance of the undertaking or termination of the obligation for which the bond or deposit was required, any amount due shall be returned by the agency concerned to the filing party, withdrawable in accordance with pertinent accounting and auditing rules and regulations. This provision shall apply to bonds posted in cash, such as bidders bond, guaranty bonds, bail bonds, judicial deposits for the benefit of clients, cash under litigation deposited in courts or quasi-judicial bodies, other refundable and judicial bonds, and all bonds and deposits required by law, rules and regulations to be posted in order to ensure faithful performance of an activity or undertaking.”

- For CY 2015, PhilSCA has Trust Liabilities in the form of cash Bid Bonds and Performance Bonds deposited as shown in Table 11 below:

Table 11.  Trust Liabilities as of December 31, 2015

| Payees | Particulars | Amount |
| --- | --- | --- |
| RJC Security and Investigation Agency, Inc. | Bid bond of Security Agency | 81,800.00 |
| RJC Security and Investigation Agency, Inc. | Performance bond-Security Services | 174,145.05 |
| Otus Copy System, Inc. | Performance bond-Purchase of Copiers & Printers | 37,832.60 |
| Prince Technologies Corporation | Performance bond-Purchase of one (1) set of Computerized Enrolment System | 300,000.00 |
| Total |  | 593,777.65 |

- Two bonds, bid security and performance bonds, were respectively received last May 24, 2010 and June 11, 2010 per Official Receipt Nos. 121907 and 125304, respectively.  Upon interview with the accounting department, these were not yet returned to the security agency since Notice of Disallowance No. 2012-164-01 (2011) dated March 2, 2012 was issued amounting to P479,031.31 pertaining on the overpayment of contract rates.

- As of December 31, 2015, the full amount of P593,777.65 remained deposited in LBP-LCCA Account No. 3562-1003-25 instead of remitting the amount to the BTr as required under Section 6 of the General Provision of 2015 GAA.

- We recommended that Management remit to the BTr the total amount of P593,777.65 pursuant to Section 6 of the General Provisions of FY 2015 GAA.

- Management commented that the authority to use all income accruing to it is by virtue of Executive Order No. 714.  SUCs are authorized under LOI Nos. 872 and 1026 to retain as Revolving Fund their income to be deposited in authorized depository bank (AGDB) and not to the account of Bureau of Treasury pursuant to Sec. 8 of the General Provisions of FY 2015 GAA.

- The team disagree with the Management comment. Section 6 of the General Provisions of FY 2015 GAA shall prevail over their cited provisions because collections of bid bonds and performance bonds are not considered as income of the College but trust receipts.

Security guard as hired contractual employees

- Since CY 2013, PhilSCA has opted to hire individuals as security guards on contract basis without employer-employee relationship incurring a total expenditures of P5,677,539.19 in CY 2015, charged from the STF instead of engaging a duly licensed security services agency, hence, may put at stake the security of the campus and stakeholders due to the absence of accountability provisions in the contract of service with individual guard, moreover, the contract is not consistent with Sections 27 and 28 of the GAA for CY 2015 and previous GAAs.

- Upon termination of the contract with ICT Security & Investigation Agency, on December 31, 2012, PhilSCA entered into contract of services with 20 individuals,  who were security guards of that security agency.  Since then, their contracts have been renewed yearly as security guards of PhilSCA hence, may compromise the security of PhilSCA, its students and personnel considering that the contractual have no security gears/equipment unlike a duly licensed security agency.  Also, these security guards are not answerable for any loss arising from their negligence in securing the properties of PhilSCA because the same was not stipulated in the contracts. Moreover, they have no employer-employee relationships with PhilSCA, negating further the possibility of recovering the loss from the erring contractual.

- In the audit it was found  that  the total  yearly  disbursements for the hiring of these individuals ranged from P4,213,594.37 to P5,677,539.19 in CY 2014-2015 which were lower than the amount they paid for CY 2011-2013 which ranged from P5,974,466.47 to P8,288,179.22 for the services of security agency.  In our views, the savings perspective could not be equated with the security of life of PhilSCA’s people and properties.

- According to Mr. Dianito Yongque, Head of Security Service-VAB Campus, they are having BAC problems when it comes to engaging with a new security agency to provide security services of well- trained security guards within the College premises.

- These scenario is not consistent with Sections 27 and 28 of the GAA for CY 2015 and previous GAAs, which provide:

Sec. 27.  Service Contracts.   All departments, bureaus and offices of the National Government, including Constitutional Offices enjoying fiscal autonomy, SUCs, GOCCs and LGUs are hereby authorized to enter into service conctracts with other government agencies, private firms, Civil Society Organizations (CSO), or individuals for services related or incidental to their respective functions and operations on part time or full time basis.

Service contracts may include the following:

- x x x

  - Janitorial, security and other related services, whenever practicable and cost-efficient to the government.

Engagement under the foregoing creates no employer-employee relationship between the agency, and the individual professional consultant private firm or CSO, or the employees of the said entities.

Sec 28.  Employment of Contractual Personnel.  Agencies of the government, including Constitutional Offices enjoying fiscal autonomy, SUCs, GOCCs, LGUs when authorized through their respective appropriations and within the limits thereof, may hire contractual personnel as part of their organization in order to perform agency functions or specific vital activities or services which cannot be provided by the regular staff of the hiring agency.

Contractual personnel employed pursuant to this section shall be considered as an employees of the hiring agency but only during the period when they reasonably required.

The total annual Personnel Services requirement for contractual personnel, to cover salaries, and other personnel benefits and fixed expenditures, shall in no case exceed the lump sum appropriations for the purpose, except when there is an urgent need to hire contractual employees in the implementation of the priority programs, activities and projects of the hiring agency, subject to approval of the DBM. In which case, the payment of compensation of contractual employees shall be sourced from the Miscellaneous Personnel Benefits Fund.

- We recommended that the Management strictly comply with the provisions of the GAA on the engaging of security services and hiring of contractuals, taking into consideration their accountability in case safety of their people and properties are at risk during their tour of duty.

- Management cited Section 27 of 2015 GAA, which authorized SUCs to enter into Service Contracts such as security and related services whenever practicable and cost-efficient to the government is their guiding principle for the PhilSCA administration in resorting to the hiring of licensed security guards as Contractual Personnel of the College.  Because of the threats post by the private security agencies which served PhilSCA in previous years proved that engaging private security agency is no longer practicable to the institution but rather they became threat to campus security.

- Rejoinder:  Hiring of contractual security personnel is cost-efficient, however, contracting security services from government recognized security agency with complete gear and security equipment licensed security guards and answerable for any loss of property and harm of PhilSCA stakeholder arising from negligence of their guards on duty is more important.

Gender and Development

Minimal accomplishment of PCW approved GAD targeted activities.

- PhilSCA utilized P2,393,897.01 or 95 percent of its allocation with only three activities accomplished out of the 17 GAD activities in the GAD Plan and Budget (GPB) hence identified gender issues and concerns in PhilSCA were not fully addressed. Moreover,  foreign travel expenses of P308,033.50 not included in the approved GPB was incurred and GAD activities were held outside PhilSCA campus whereby PhilSCA incurred hotel accommodation of P297,000.00.

- Pursuant to R. A. 9710 or the Magna Carta of Women and the GAA of 2015, all government departments, including their attached agencies, offices, bureaus, State Universities and Colleges (SUCs), Government Owned and Controlled Corporations (GOCC), Local Government Units (LGUs) and other government instrumentalities shall formulate their annual GPBs within the context of their mandates to mainstream gender perspectives in their policies, programs and projects.  GAD Planning shall be integrated in the regular activities of the agencies, the cost of implementation of which shall be at least five percent (5%) of their total budgets.  The computation and utilization shall be implemented in accordance with specific guidelines provided therein

- COA Circular No. 2012-003 dated October 29, 2012, provides the Updated Guidelines for prevention and disallowance of Irregular, Unnecessary, Excessive, Extravagant and Unconscionable Expenditure.

- While, 3.1.1.8 of the COA Circular No. 96-004 dated April 19, 1996, provides that:  To ensure that government funds and property are used only for official purposes, no reimbursement of the cost of gasoline and oil shall be allowed if a private vehicle is used. However, the officials and employees concerned shall be entitled to the reimbursement of the equivalent cost of the customary mode of transportation. Under no circumstances should fuel be issued to privately owned motor vehicles.

- For FY 2015,  PhilSCA has a total appropriation of P87,774,000.00 of which at least five percent or P4,388,700.00  would have been budgeted for GAD program and activities; however, the College actually allocated P2,520,000.00 or 2.9 percent of total appropriation in the approved GAD Plan and Budget.

- The Philippine Commission on Women (PCW) endorsed the PhilSCA Annual GAD Plan and Budget of P2,520,000.00 on April 16, 2014 prepared to address the following gender related issues/concerns, as shown in Table 12 below:

- Table 12.  2015 PhilSCA Plan and Budget

| GAD Activities | Output Performance Indicators and Targets | Total Budget Per Activity |
| --- | --- | --- |
| - Conduct of two (2) day Gender Sensitivity Seminar with Integration of VAW laws for students faculty and admin personnel of 4 PhilSCA campuses | 1 batch of Gender Sensitivity Seminar to be conducted by 2nd Quarter | 450,000.00 |
|  | 3,000 students and 290 faculty and administrative personnel oriented on GAD issues and concerns, and laws on women (4 PhilSCA Campuses) |  |
| - Posting of updates in the GAD Advocacy Corner or as the need arises: Semi-annual updating of the advocacy corner of the four (4) campuses | 4 Advocacy corners updated with all gender issues -e.g. Latest news on women, thematic concepts like nutrition, mother's day, earth month, etc. In 4 campuses | 15,000.00 |
| - Conduct of Advocacy Forum in the Aviation Industry | Two (2) advocacy forum for aviation industry conducted | 240,000.00 |
|  | 150 personnel from the different local airlines operating in Manila, MIA and NAIA airport participated |  |
| - Conduct of two day Gender Sensitivity Seminar with integration of RA 7877 for students and faculty and admin personnel of 4 PhilSCA campuses | VAB Campus, Villamor Main Campus for 1000 students and 175 faculty and admin personnel participation in the seminar | 410,000.00 |
|  | FAB Campus , Lipa City for 500 students and 45 faculty and admin personnel participation |  |
|  | BAB Campus, Floridablaca, Pampanga for 500 students and 42 faculty and admin personnel participation in the seminar |  |
|  | MBEAB Campus, Lapu-lapu City Cebu for 600 students and 57 faculty and admin personnel participation in the seminar |  |
| - Publication of Standard Operating Procedures | Five (5) Standard Operating Procedures | 50,000.00 |
| - Conduct of workshops to identify gender issues/GAD core messages and how these can be integrated in the curriculum targeting the syllabus of the general education subjects (use gender issues in certain subject like English, Psychology, etc | One (1) seminar/workshop on gender integration in curriculum conducted | 130,000.00 |
|  | 10 syllabus integrated with gender |  |
| - Conduct of forum on Adolescent and reproductive health issues and perspectives in all PhilSCA campuses | Four forum on Adolescent and reproductive health issues and perspective conducted | 80,000.00 |
|  | 84 faculty members, 49 Admin personnel and 2,500 students attended and participated in the forum for the four campuses |  |
| - Research or survey activity by the teaching and non-teaching personnel | One research conducted and published | 75,000.00 |
| - Develop and publish a GAD newsletter and research journal | Two GAD newsletter and research journal published | 150,000.00 |
| - Conduct of the following with set theme: | Eight tarpaulins hanged/displayed | 175,000.00 |
| a. Art exhibit on ten women who contributed in the development of the country | Four film showing conducted, 1 photo/art exhibit, 1 forum/seminar on reproductive rights conducted, 50 faculty members, 40 admin personnel, 2,500 students and 500 participation of women in the barangay |  |
| b. Film Showing |  |  |
| c. Seminar/Forum in connection with the women month theme |  |  |
| - Information dissemination through flyers and leaflets during flag ceremonies for whole month of March | 5,000 leaflets distributed in four campuses | 30,000.00 |
| - Recognition of empowered women in academe. One faculty and one admin personnel for each campus | One faculty and 1 admin personnel recognized | 35,000.00 |
| - Conduct of Info drive on VAW in different PhilSCA campuses | Four info drive conducted, 2 IEC materials develop and distributed | 50,000.00 |
| - Conduct of GST ++ for PhilSCA GFPS members | 40 GFPS members trained | 350,000.00 |
|  | 1 GST ++ for GFPS conducted |  |
| - Attendance and participation to seminar sponsored by other agencies | Five Seminars attended outside PhilSCA | 100,000.00 |
| - Development of Sex-disaggregated database | 90% sex disaggregated data completed | 100,000.00 |
| - Setting of child minding and lactation room for PhilSCA employees in all campuses, VAB, FAB, BAB and MBEAB Campuses | One room allocated for child minding and lactation | 80,000.00 |
| Total |  | 2,520,000.00 |

- Verification of the Registry of Allotment and Obligation revealed a total obligations for GAD totaling P2,393,897.01 consisting of Fund 101 of P1,728,422.01 and Fund 164 of P665,475.00 or a 95 percent utilization of the approved budget of P2,520,00.00 although only three activities were accomplished out of the 17 activities in the PWC endorsed GPB.  It was further observed that the expenses for the two activities exceeded their budgets and PhilSCA incurred expenditures amounting to P135,787.23 for GAD related activities but not included in the PCW endorsed GPB. The details are as follows:

- Three accomplished activities with expenses of the two activities exceeding the budget as shown below:

Table 13.  2015 Accomplished GAD Activities

| Activities per GPB | Budget | Actual GAD Activities | Amount Spent | Under (Over) |
| --- | --- | --- | --- | --- |
| Conduct of 2-day Gender Sensitivity Seminar with Integration of VAW laws for Students, faculty and Administrative Personnel of 4 PhilSCA campuses | 450,000.00 | Conduct of Gender and Development with Disaster Risk Reduction Seminar on April 17, 2015 at Pajo Gynasium, Lapu-lapu City | 98,500.00 |  |
|  |  | International Women's Men with Gender Sensitivity Training -FAB Campus held at La Virginia Hotel and Resort, Mataas na kahoy, Batangas on March 26-28, 2015 | 297,000.00 |  |
|  |  | Training on Men Talking about Men on Feb. 6-8, 2015 at Hotel Kimberly, Tagaytay City | 163,000.00 |  |
|  |  | Total | 558,500.00 | (108,500.00) |
| Conduct of GAD Advocacy Forum in the aviation industry | 240,000.00 | Pre-second semester coordinating conference at PhilSCA Villamor Campus, Pasay City on October 19, 2015 (Moved to Oct. 20, 2015) GAD Issues and Concerns; Low level of awareness and understanding of GAD issues and concerns, laws on woman among partner airline companies, GA and NGAs, etc. | 201,262.40 | 38,737.60 |
| Attendance and participation to seminar sponsored by other agencies | 100,000.00 | Travelling expenses in attending 4th National GAD Conference on Sept.29-Oct.3,2015 at Puerto Princesa Palawan |  |  |
|  |  | Dr. Rowena S. Navera | 26,217.12 |  |
|  |  | Estrella E.Yago | 13,448.24 |  |
|  |  | Noel E. Lagui | 7,738.12 |  |
|  |  | Jahaziel I. Vargas | 8,724.12 |  |
|  |  | Jay Jack R. Manzano | 6,834.52 |  |
|  |  | Felix C. Boyles | 7,956.12 |  |
|  |  | Ginalyn P. Cordovilla | 8,864.12 |  |
|  |  | Travelling expenses to attend 4th GAD National Conference at City State Asturias, Puerto Princesa | 26,217.12 |  |
|  |  | Travelling expenses to attend Public Orientation on CHED Memorandum Order No. 1 s. 2015 entitled Establishing the Policies and Guidelines on Gender and Development for CHED and Higher Education Institution | 15,287.75 |  |
|  |  | Total travelling Expenses | 127,287.23 | (27,287.23) |

- Incurred expenditures of P308,033.50 for activities not included in the GPB.  This is the foreign travel of Dr. Rowena Navera to the 59th Session of the United Nations Commission on Status of Women in Beijing on March 4-20, 2015.

- Approved GAD activities not accomplished

Shown in Table 14 are the unaccomplished activities in CY 2015:

Table 14.  2015 Unaccomplished GAD Activities

| GAD Approved Activity | Approved Budget |
| --- | --- |
| - Posting of updates in the GAD Advocacy Corner or as the need arises |  |
| Semi-annual updating of the advocacy corner of the four (4) campuses | 15,000.00 |
| - Conduct of workshops to identify gender issues/GAD core messages and how these can be integrated in the curriculum targeting the syllabus of the general education subjects (use gender issues in certain subject like english, psychology, etc. | 130,000.00 |
| 3. Conduct of forum on Adolescent and reproductive health issues and perspectives in all PhilSCA campuses | 180,000.00 |
| - Conduct of two day Gender Sensitivity Seminar with integration of RA 7877 for students and faculty and admin personnel or 4 campuses | 410,000.00 |
| - Publication of 5 standard operating procedures | 50,000.00 |
| - Research or survey activity by the teaching and non-teaching personnel | 75,000.00 |
| - Develop and publish a GAD newsletter and research journal | 150,000.00 |
| - Conduct of the following with set theme: |  |
| - Art exhibit on ten women who contributed in the development of the country |  |
| - Film Showing |  |
| - Seminar/Forum in connection with the women month theme | 175,000.00 |
| - Information dissemination through flyers and leaflets during flag ceremonies for whole month of March | 30,000.00 |
| - Recognition of empowered women in academe. One faculty and one admin personnel for each campus | 35,000.00 |
| - Conduct of Info drive on VAW in different PhilSCA campuses 10. | 50,000.00 |
| - Conduct of GST ++ for PHilSCA GFPS members | 350,000.00 |
| - Development of Sex-disaggregated database | 100,000.00 |
| - Setting of child minding and lactation room for PhilSCA employees in all campuses |  |
| Total | 1,750,000.00 |

- The non- accomplishment of the 14 GAD activities or 82 percent of the 17 GAD approved activities resulted in Management’s failure to address majority of the related gender issues and concerns of PhilSCA.

- Training on Men Talking about Men on Feb. 6-8, 2015 at Hotel Kimberly, Tagaytay City and the Gender Sensitivity Training of PhilSCA –FAB held in La Virginia Hotel and Resort on March 26-28, 2015 whereby the agency spent P460,000.00 conducted outside PhilSCA campus that could have been done within their campus.

- Included in her liquidation of cash advance were the expenses on the foreign travel of Dr. Navera to New York, USA, an activity not included among the approved 2015 GAD Plan and Budget activities.

- We recommended that the Management:

- require the Chair, GAD Focal Point System, to see to it that GAD planned activities were accomplished fully to address the identified gender issues and concerns in PhilSCA;

- see that GAD allocated funds were spent as budgeted in accordance with laws, rules and regulations, and

- plan and conduct GAD program and activities with prudence towards addressing the gender issues.

- The GAD Focal Person commented that majority of the GAD activities included in GPB were not implemented because the operational Plan for every Activity were not acted upon by the Office of Vice President for Administration and Finance (VPAP).

- Rejoinder:  It is only but proper for VPAP to review and decide how the fund of PhilSCA be spent economically and effective in accordance to their mandate and priority.

Senior Citizens and Persons with Disability

- Like in previous years, PhilSCA did not allocate from its approved budget nor prepare/formulate corresponding plans, program and projects to address the concerns of the Senior Citizens (SC) and Persons With Disability (PWD) in the College, contrary to Section 35 of the General Provisions of RA No. 10651 or the GAA for FY 2015.

- Section 35 of the General Provisions of RA No. 10651, the GAA for FY 2015 provides that all agencies of the government shall formulate plans, programs and projects intended to address the concerns of Senior citizens and persons with disability, insofar as it relates to their mandated functions and integrate the same in their regular activities.

- Learned from inquiry with the Director for Extension Service that until now PhilSCA has no responsible unit and official assigned to initiate formulation and implementation of plans, program and projects to address concerns of SC and PWD.

Compliance with Tax Laws

- PhilSCA was able to withheld and remit taxes in CY 2015,  in compliance  with the Bureau of Internal Revenue (BIR) Tax Revenue Regulation No. 10-2008 dated July 8, 2008 for compensation and Revenue Memorandum Circular No. 23-2007 dated March 23, 2007 for government money payment due or payable to all suppliers of goods and/or services.

- As of December 31, 2015, the Due to BIR account has a balance of P1,796,255.67 of which P607,460.56 was remitted on January 11, 2016 under Check Nos. 64924 to 64926 dated January 7, 2016. Summary of Taxes Withheld and Remittance for the year is as follows:

- Table 15. Summary of Taxes Withheld and Remittance for the Period of

- January 1 to December 31, 2015

| Period | Withheld | Remittance | Unremitted Balance |
| --- | --- | --- | --- |
| Beginning Balance |  |  | 1,440,962.79 |
| January | 529,655.85 | 1,164,465.67 | 806,152.97 |
| February | 839,501.90 | 1,064,069.68 | 581,585.19 |
| March | 1,113,556.82 | 922,859.78 | 772,282.23 |
| April | 851,951.56 | 1,121,697.76 | 502,536.03 |
| May | 603,813.66 | 768,821.23 | 337,528.46 |
| June | 635,317.04 | 556,977.90 | 415,867.60 |
| July | 905,125.64 | 621,182.05 | 699,811.19 |
| August | 1,363,188.71 | 930,765.82 | 1,132,234.08 |
| September | 1,292,883.55 | 1,563,694.01 | 861,423.62 |
| October | 1,006,654.02 | 1,155,651.34 | 712,426.30 |
| November | 721,892.79 | 928,323.04 | 505,996.05 |
| December | 1,695,364.17 | 405,104.55 | 1,796,255.67 |
| Total | 11,558,905.71 | 11,203,612.83 |  |

- Compliance with RA No. 8291 on proper deductions and remittances of GSIS premiums

- For CY 2015, PhilSCA withheld a total of P8,016,519.87 and remitted P7,359,477.52 in GSIS premiums from its officers and employees in compliance with the GSIS Law.

- The summary of the premiums withheld and remitted under account Due to GSIS is shown below:

Table 16. Share of GSIS Employees’ and Employers’ Share and Remittance

| Period | Total Employees' Share | Total Employer’s Share | Total Employees’ and Employer’s Share | Remittance to GSIS |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | GSIS Official Receipt No. / Date | Amount Remitted |
| Beginning Balance | - | - | - | - | - |
| January | 273,646.35 | 379,235.06 | 652,881.41 | 003600017379 / February 9, 2015 | 652,881.41 |
| February | 273,646.35 | 377,720.78 | 651,367.13 | 2550051038 / March 9, 2015 | 651,367.13 |
| March | 299,741.31 | 414,114.06 | 713,855.37 | 2700065232 / April 8, 2015 | 713,855.37 |
| April | 286,719.21 | 395,751.26 | 682,470.47 | 2550053175 / May 7, 2015 | 682,470.47 |
| May | 278,833.95 | 384,937.58 | 663,771.53 | 3450070010 / June 8, 2015 | 663,771.53 |
| June | 286,914.78 | 395,912.02 | 682,826.80 | 2700071026 / July 7, 2015 | 682,826.80 |
| July | 280,217.97 | 386,882.94 | 667,100.91 | 2550057192 / August 10, 2015 | 667,100.91 |
| August | 278,423.37 | 384,390.14 | 662,813.51 | 3000054798 / September 8, 2015 | 662,813.51 |
| September | 278,441.73 | 384,414.62 | 662,856.35 | 3000056034 / October 8, 2015 | 662,856.35 |
| October | 278,459.82 | 384,438.74 | 662,898.56 | 3450077328 / November 3, 2015 | 662,898.56 |
| November | 275,818.50 | 380,816.98 | 656,635.48 | 2700078741 / December 7, 2015 | 656,635.48 |
| December | 275,992.87 | 381,049.48 | 657,042.35 | 2700080797 / January 8, 2016 | 657,042.35 |
| Total | 3,366,856.21 | 4,649,663.66 | 8,016,519.87 |  | 8,016,519.87 |

- The employees’ and employer’s contributions totaling P657,042.35 for the month of December 2015 were entirely remitted on January 8, 2016 per Check Nos. 83956-83957 dated December 21, 2015.

- The ending balance as of December 31, 2015 in the amount of P140,691.92 represents the additional GSIS Premium deductions brought about by the NBC 461 Cycle 4 Salary Differential of PhilSCA Faculty which was booked as Accounts Payable as of December 31, 2015 and still awaiting for the release of NCA from DBM as of this writing.

Status of Settlement of Audit Suspension and Disallowances

- Total suspensions and disallowances as of December 31, 2015 as reflected in the Statement of Audit Suspension, Disallowances and Charges (SASDC) amounted to P21,859,178.10, as follow:

| Particulars | Suspensions | Disallowances |
| --- | --- | --- |
| Beginning Balance, January 1, 2015 | 0.00 | 3,227,878.10 |
| Add: Issuances during the year | 18,631,300.00 | 0.00 |
| Total | 18,631,300.00 | 3,227,878.10 |
| Less: Settlements during the year | 0.00 | 0.00 |
| Balance, December 31, 2015 | 18,631,300.00 | 3,227,878.10 |

- For the unsettled disallowances as of December 31, 2015, two of the liable persons submitted appeal for exclusion from liability and still awaiting for resolution of the Commission. While for the suspension of P18,631,300.00, Management submitted to the audit team documents/justification, which are now for evaluation.