STATUS OF IMPLEMENTATION BY MANAGEMENT OF PRIOR YEARS’ AUDIT RECOMMENDATIONS

Out of seventeen prior years’ recommendations, two were fully implemented, 12 were partially implemented and three were not implemented, details of which are presented below.

| Observations and Recommendations | ## Ref. | Management’s Acton/Reply | Status of Implementa-tion | Result of Auditor’s Validation |
| --- | --- | --- | --- | --- |
| - Only P3.568 million or 13.88 percent out of the P25.704 million STF budget for Capital Outlay was utilized resulting in failure to address the need of the College for a modern and improved facilities due to deficient planning, budgeting and execution of procurement activities which is evident further by the absence of time lines, mode of procurement and other required data in the Approved Procurement Plan and the frequent resorting to small value procurement/ shopping methods for similar items which if procured in bulk may be more advantageous to the government. We recommended and Management agreed to: - be more meticulous and judicious in planning the procurement projects and ensure full implementation thereof as well as the efficient utilization of the budget in compliance with RA No. 9184; - prepare an APP that is sufficient in form and substance following the requirements of the same RA, and - justify why the college had adopted alternative modes of procurement through shopping and small value procurement instead of public bidding. | Para. 10-15 Pages 33-37 AAR 2014 Para. 1-9 Pages 20-22 AAR 2013 | Complied with - CHED Memorandum and COA Circular in the preparation of the budget proposal for approval by the BOT. | Partially Implemented | Certification of Chief Accountant that sufficient cash is available to cover 2015 STF funding requirement not yet complied. |
| - The College overshot its approved budget for extension services of P400,000.00 by 108 percent or P433,299.18 due to: a) unreasonable number of at least 15 travelling personnel per training activity resulting to travelling expenses of P347,311.00, b) approving reimbursement of expenses as a common practice totaling P272,960.26 and c) incurrence of unnecessary expenses of P48,800.00 for snacks and meals thus, resulting to uneconomical spending of government resources. We recommended that the Management submit the BOT post approval for the incurrence of expenditures beyond the budget as well as the accomplishment reports of those who have travelled and submit valid justification for a) authorizing the travel of 15 -17 personnel in the same activity; b) reimburse-ment of expenses; and c) charging from the College Fund the food expenses incurred. Henceforth, spend within the budget, limit the number of travelling personnel and discontinue the practice of reimbursement of expenses which are not allowable in audit. | Para. 16-23 Pages 33-37 AAR 2014 Para. 24-34 Pages 40-44 AAR 2014 Para. 24-32 Pages 27-30 AAR 2013 |  | Partially Implemented | Reiterated in paragraphs 5.1-5.7 of this report. |
| - Out of the 35 potential student-grantees allocated to PhilSCA for Academic Year (AY) 2014-2015 for the Expanded Students’ Grants-in-Aid Program for Poverty Alleviation (ESGP-PA) with an appropriation of P2,182,000.00, only 20 were enrolled in the three campuses but only seven were actual grantees who were included in the validated Master List of the DSWD-NCR while the 13 are still for approval by the DSWD-NCR, hence the amount of P432,600.00 was obligated, thereby leaving an unutilized balance of P1,749,400.00 as of December 31, 2014. We recommended and Management agreed to: - coordinate closely with DSWD-NCR for the immediate validation and approval of the remaining 13 enrolled students; - facilitate the release of NCAs and scholarship grants to the students; and - address the issues and concerns affecting the effective implementation of the said Program at PhilSCA. | Para. 35-42 Pages 45-47 AAR 2014 | PhilSCA management had coordinated with DSWD-NCR already. | Partially Implemented | Still, the target of 35 potential student grantees were not met. The unutilized balance of P1,749,400.00 still not fully utilized in CY 2015 |
| - The Budget Officer did not fill up the line item data on MOOE and Capital outlay approved budget and unutilized budget but only the total per class of expenditure and also committed error in presenting the total capital outlay budget as approved by the BOT of P22,904,702.00 as P25,704,702.00 or a difference of P2,800,000.00 in the Statement of Approved Budget, Utilizations, Disbursements and Balances by Object of Expenditures (FAR No. 2-A) under COA-DBM Joint Circular No. 2014-1 dated July 2, 2014, which rendered unreliable and incomplete the said budgetary report as well as the concealed information on the incurrence of overdrafts per object of expenditure. We recommended and Management agreed to revise the SABUDBOE to include the required data in the columns for approved budget and unutilized budget and to correct the misstatement in the total of the Capital Outlay account. Henceforth, observe completeness and transparency in the filling up of data in the budgetary report. | Para. 43-47 Pages 47-49 AAR 2014 |  | Not Implemented | Line item data on PS, MOOE, CO on FAR No. 2-A of CY 2015 still not presented in the report. |
| - Contrary to the Audit Team’s prior year’s recommendation to stop giving additional benefits without legal basis or DBM authority, PhilSCA continued granting Personnel Welfare & Benefits (PWB) in the form of “Best Organizational Unit Award” to all its personnel and extended 13th Month Pay in CY 2014 to personnel, student assistants, and security guards under job order/contractual basis without employee-employer relationship amounting to P8,554,353.16 charged from the STF resulting in audit disallowance totaling P27,235,653.16 (for CY 2012, 2013 & 2014) due to violation of Civil Service Commission (CSC) Resolution No. 010112 dated January 10, 2001, RA 8292 and the Salary Standardization Law of 2009 (Joint Resolution No. 4 s. 2009 of the Senate and the House of the Representatives). We recommended that Management: - stop the practice of giving out incentives/benefits to its employees chargeable against the STF without legal basis and appropriate supporting documents; - submit the documentary requirements on the Notice of Suspension issued and require the persons liable to refund based on the Notice of Disallowance. | Para. 48-61 Pages 49-53 AAR 2014 Para. 10-23 Pages 22-27 AAR 2013 | Granting of PWB is stopped in CY 2015, | Partially Implemented | Required documents in compliance with the issued Notice of Suspension are yet to be submitted. |
| - PhilSCA has not yet addressed the recurring deficiencies in property management as proven by the a) continued inadequacy of records in the Accounting and Property Sections both of which did not maintain the required Property, Plant and Equipment ledger card (PPELC) and the Property Cards; b) incomplete conduct of physical inventory taking wherein the latest is for CY 2013; and c) unreliable inventory report showing an unreconciled difference of P36,056,560.72 as against the book balance of even date, thereby resulting in the high risk of loss of depreciable assets without detection and rendering their doubtful existence and validity of the book balance totaling P150,914,771.54 as of December 31, 2014. We recommended and Management agreed to: - give preferential attention on improving the internal control on property management by strictly complying with the aforesaid rules and regulations. In case of continued non-compliance thereof, enforce firmly the corresponding legal sanctions against the concerned personnel for neglect of duty; - conduct the required annual inventory taking, the result of which should be reported in a duly accomplished and timely submitted RPCPPE which should be reconciled with the records of the Accounting Section; - maintain PPELC and Property Cards which should be regularly updated and reconciled by the concerned offices; and - require the Property Officer to renew the ARE every three years or every time there is a change in accountability. | Para. 63-69 Pages 53-69 AAR 2014 | Completed 2014 Physical Inventory in four PhilSCA campuses | Partially Implemented | Balance per record of accounting and property not yet reconciled |
| - PhilSCA incurred total expenditures of P1,935,615.93 that is more than the approved budget of P1,850,000.00 although 13 approved activities with a budget of P980,000.00 were not undertaken, of which P374,667.38 was incurred for personnel’s training/seminars conducted at the resort, and the amount of P46,000.00 was spent on seminars for local/Barangay officials and their constituents, hence not within the concerned sector of the College. We recommended and Management agreed to: - disburse the GAD funds within the approved budget and only for activities that will address gender issues within the College’s concerned sectors or mandate avoiding the use of expensive outside facilities/venue to save funds; and - submit justification for incurring expenditures in excess of the budget despite the non-implementation of the 13 activities. | Para. 70-76 Pages 56-62 AAR 2014 Para. 78-87 Pages 46-51 AAR 2013 |  | Partially Implemented | Reiterated in paragraphs 11.1- 11.9 of this report. |
| - The Disbursement Acceleration Program funds transferred from CHED in CY 2012 in the amount of P3.23 million was entirely disbursed by PhilSCA in the same year for the procurement of 80 computers and peripherals from the Procurement Services of DBM. However, the envisioned aim of the DAP to upgrade and modernize the facilities of PhilSCA to accelerate the delivery of instruction was not realized because the initial delivery of the 52 out of the 80 computers were made only on May 8, 2014; hence, the students of the Institute of Computer Studies (ICS) for school year 2013-2014 were deprived of the use of upgraded computers. We recommended and Management agreed to: - make urgent representation with PS-DBM for the immediate delivery of the remaining computers, servers, printer and other items paid in advance; and - ensure the maximum utilization of the delivered computer equipment by the students of ICS for a more improved instruction services of PhilSCA. | Para. 33-41 Pages 30-32 | All the remaining computers were fully delivered and accounted for and the same were utilized by ICS. | Fully Implemented |  |
| - Due to the absence of development and building/ structure plans, detailed construction cost per building/structure and other pertinent documents from the MEGAWORLD, the agency has not yet issued the Certificate of Acceptance as basis to book up the assets in the books of accounts resulting in unreliable balance of the Office Buildings and School Building accounts, both with zero balance as of December 31, 2013. Moreover, the absence of the Certificate of Acceptance has delayed the process for the transfer of title of the Campus site in the name of PhilSCA pursuant to the land swapping arrangement among PhilSCA, BCDA and MEGAWORLD covered by Memorandum of Agreement (MOA) dated June 10, 2010 which may affect their legal right of ownership. We recommended and Management agreed to closely coordinate with the BCDA to obtain the development and building/ structure plans, detailed construction cost per building/structure and other pertinent documents from the MEGAWORLD; and ascertain the structural soundness of the buildings and structures and identify defects, if any, for Megaworld to rectify in order to fast track the issuance of Certificate of Acceptance by the Management. | Para. 42-55 Pages 32-37 AAR 2013 Para. 1-17 Pages 18-23 AAR 2012 | PhilSCA management exert extra effort to coordinate with BCDA and Megaworld. | Partially Implemented | Certificate of Acceptance was not yet issued due to failure to secure the required plans and pertinent documents from Megaworld, thus the Office and School Buildings constructed by Megaworld are still unrecorded and transfer certificate of title for the swapped lot not yet in the name of PhilSCA. |
| - Management failed to strictly implement COA Circular No. 2012-004 dated November 28, 2012 resulting in a minimal reduction of 14 percent or P123,352.35 of the unliquidated cash advances of P865,450.78 as of December 31, 2011 of individuals no longer connected with PhilSCA, whose remaining cash advances of P742,098.43 are still recorded as Advances to Officers and Employees Account instead of Other Receivables account. Moreover, they have the practice of granting additional cash advances to accountable officers without requiring the liquidation of the previous ones thus exposing the funds to misuse. We recommended that Management: - comply strictly with the procedures in COA Circular No. 2012-004 dated November 28, 2012, including the filing of appropriate charges against the defaulting accountable officers. For those cash advances which are deemed impossible to collect after exerting best efforts, request for the writing off pursuant to COA Circular No. 97-001 dated February 5, 1997; and - refrain from granting additional cash advances for those with outstanding cash advances as well as extending cash advances for infrastructure project and ensure that all cash advances are liquidated within the required due dates, in accordance with COA Circular No 97-002. | Para. 56-64 Pages 37-40 AAR 2013 Para. 18-31 Pages 24-27 AAR 2012 | Management wrote a letter request to the COA for write off of unliquidated cash advances to individuals who are no longer connected with PhilSCA and cannot be recovered. | Partially Implemented | Balances for Advances to Officers and Employes reduced to P5,964.68 from P18,209.54 in prior year. |
| - There were 39 Petty Cash custodians during the year, of which: a) 18 have existing petty cash funds (PCF) of P112,716.35 as of December 31, 2013, P39,998.00 thereof belongs to two former employees who were already resigned or on AWOL whose PCFs were established six to 20 years ago; b) 34 have petty cash fund of P4,999.00 each to avoid the bonding requirement, majority or 29 of them, which included the Accountant and the Budget Officer, were not bonded and expenses incurred were mostly on meals for their office meetings; and c) three AO made payments out of their Petty Cash Fund for expenses that exceeded the P15,000.00 limit of each transaction or for payment of the payroll of laborer and travelling allowances/expenses contrary to existing regulations. We recommended and Management agreed to: - limit to one PCF for each campus whose custodian should be properly bonded and knowledge-eable on the proper procedures in the handling of PCF including the bookkeeping of transactions; - observe the existing rules and regulations in the disbursement as well as replenishment of the PCF. Charge from the representation allowance of the heads of office food expenses during their meetings; and - reclassify the balance of PCF of the two former PhilSCA personnel from Petty Cash Fund account to Other Receivables account and exert best efforts for the return of those balances. | Para. 72-77 Pages 42-46 AAR 2013 | Management reduced the number of Petty Cash Custodian from 39 to only 3 As of Dec. 31, 2014. | Partially Implemented | Only two Petty Cash custodians refunded the full amount of their accountability on January 2015. |
| - The accountabilities/ cash shortages of the two former Cashiers of PhilsCA were not properly booked-up resulting in the overstatement of Cash- Collecting Officer account by P107,504.05, misstatement of Prior Year Adjustments Account by P51,477.27 and understatement of the Other Receivables Account by P158,981.32, which represents the total accountability and which has not yet been settled to date, thus may result to loss of government funds. We recommended that Management: - initiate immediately legal remedies to recover the funds from Ms. Palado and from the heirs of the late Ms. Daligdig to protect the interest of the government. | Para. 24-31 Pages 25-27 AAR 2012 AAR 2011 AAR 2007 | The husband of the late Ms. Evangeline Daligdig partially settled the amount of P28,780.79 leaving a balance of P34,261.77 | Partially Implemented | No additional payment was made in CY 2014-2015. |
| - Two Tampico trainer planes of the College have remained grounded or unutilized since 2008 because of the failure of the management to secure from the Civil Aviation Authority of the Philippines (CAAP) the Certificate of Airworthiness Directive (CAD) and Aviation Training Organization Certificate (ATOC), as requirements to operate a Flying School, thus resulting in the non-achievement of the College’s mandate to provide advance level of instructions in the field of aeronautics, loss of income of P13.96 million for the training of eight qualified student pilots for Private and Commercial Pilot Courses that were outsourced from private flying school; continuous incurrence of unnecessary expenses for the planes maintenance of P2.17 million and under-utilization of key personnel of the Flight and Ground Training Section. In order for PhilSCA to attain fully its mandate, gain income, prevent incurrence of unnecessary expenditures and maximize the utilization of its key Flight Personnel, we recommended that management: - secure Aviation Training Organization Certificate from CAAP - comply with the requirements of the CAAP by upgrading the airworthiness condition of the two Tampico trainer planes, if feasible; and - make representation with the Office of the President and the Department of Budget and Management for the inclusion of budget for the procurement of new trainer planes. | AAR 2010 AAR 2011 Para. 40-53 Pages 29-33 AAR 2012 | Management requested CAAP for the issuance of CAD and already performed preliminary test flight of one of their trainer planes. Representation with Sen. Pia Cayetano was initiated by PhilSCA for inclusion of appropriation for acquisition of new trainer planes in the 2016 GAA. | Partially Implemented | CAD and ATOC from CAAP are still not secured. |
| - The continued practice of accumulating collections, totalling P4.6 million, from two to six days instead of depositing intact daily as required under Section 21 of the Manual on NGAS, Volume I, exposed government funds to the risks of possible losses and misappropriations. Recommendation: We reiterate our recommendation that Management instruct all Collecting Officers of all campuses, particularly that of BASA Air Base and Fernando Air Base, to deposit all their collections intact as prescribed and strictly adhere to the provisions of Section 21 of the NGAS Manual, Volume I, to avoid possible losses or misuse/misappropriation of funds. | AAR 2011 | In Fernando Air Base, collection were already deposited intact. | Fully Implemented |  |
| - The need to enhance the collection efficiency of the College as receivables from: a) unpaid tuition fees of P1.15 million for SY 2011-2012; b) overdue lease/rentals of P76,500; and c) disallowances of P299,407.25 remained uncollected for 61 days to 365 days which may adversely affect its operational budget under the special trust fund and may incur losses from bad debts. Recommendations: - prepare and submit for approval to the Board of Trustees, written policies and guidelines on minimizing or eliminating outstanding balances of tuition fees of delinquent students and reduce leases/rental IGPs with emphasis on billing, collecting, monitoring, accounting and reporting; - adopt strict collection written policies/measures such as imposition of penalty and interest on delinquent students and lessees; and - send immediately and regularly thereafter, demand letters to students and concessionaires with unpaid obligations. | AAR 2011 | Continuous refunds of the audit disallowances are effected thru salary deductions except those members of the BOT who are not organic employees of PhilSCA. | Partially Implemented | The Management admitted that they were helpless in enforcing the collection of unpaid tuition fees since students were allowed to take their examinations even with outstanding obligations due to CHED policy not to prevent any student to take final exam. |
| - The College failure to integrate in its regular activities, plans, programs and projects intended to address the concerns of senior citizens, provide facilities for the differently-abled persons and to allocate funds of at least one percent or P615,581.00 of its P61.56 million budget was inconsistent with Sections 32 and 34 of the General Appropriations Act (GAA) of 2011 or R.A. 10147, thus, defeating its purpose to address the needs of the intended beneficiaries. Recommendations: - comply strictly with Sections 32 and 34 of the general provisions of the General Appropriations Act of 2011; and - give priority to the implementation of the programs/projects related to senior citizens and the differently-abled persons and provide facilities for them that shall enhance their mobility, safety and welfare. | AAR 2011 | Recommenda- tions not yet complied by PhilSCA management | Not Implemented | Reiterated in paragraph 12 of this report. |
| - Deficiencies were noted in the implementation of the rental of spaces/stalls operation that contributed to their failure to collect unpaid rentals of P382,500 from 27 stallholders which, if not immediately addressed properly, may weaken the viability of the College to sustain and augment its financial undertakings. Recommendations: - prepare written policies on Income Generating Projects to be reviewed and approved by the Board of Trustees for proper implementation of the concerned unit/ division; - strictly follow Section 533 of GAAM Volume II on the renewal of revenue-generating contracts, and - consider the possibility of revising the contract to be inclusive of utility charges or cause the installation of separate electric/water sub meters as well as provisions for penalty/surcharges for delayed/non-payment of rent, and security or advance deposits to answer for possible damages to the PhilSCA property and other important provisions, - send demand letters to stallholders with unpaid rentals; - demand for the cancellation of contracts of delinquent stallholders and blacklisting them for future similar transactions, - comply with our previous year’s audit recommendations: - require the Accounting Office to prepare and issue billing statements for all stall owners to monitor easily the collection of rental income. Exert all efforts to collect the rental from the Diaz canteen and other food stall owners; and - formalize contracts with all occupants of college spaces and enforce collections due from them. | AAR 2010 |  | Not Implemented | Management failed to collect the unpaid rentals of P382,500.00 from stallholders in old PhilSCA-VAB campus, management cannot issue demand letter due to the absence of last known address of debtors. |